## Hoja1
Activity | Who | Deadline
Decision tree for objectives -> indicators -> Data needed -> analysis -> results -> recommendations | All
Propose 2 ways to present the results (fast and in depth) | All | July 2nd
Propose one way to use all the governance data (each) | All | July 2nd
Specify how "natural disturbances" will be incorporated | All
Final table of indicators including comments by COBI, EA, and extra columns | Caio | June 26
Match objectives to indicators | Caio + Melaina | TBD
Interviews | COBI + JC | All summer long!
Unified biophysical databases | COBI + JC | TBD
Guidebook formating | Jael | August 13rd
Include Fio's part (https://michelilab.stanford.edu/micheli) | Jael | Done
Tough, in depth description of each indicator (for the guidebook) | Jael | August 13rd
Translate webpage to spanish | Jael | July 12nd
Compile all the information in the ETJ | Jael + JC | July 6
Look-up tables that link DBs | JC | July 1st
Modify R package to include new functions for new indicators, and allso for more flexibility | JC | June 28
Update Vignette of R package | JC | July 1st
Double-check R package | Melaina + JC