## Hoja1
Who | ColorCode
GP / Unassigned
COBI
Caio
Melaina
JC |  |  |  |  | Year: | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017
Jael |  |  |  |  | Month: | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6
Activity | Start dd/mm/yyyy | Due dd/mm/yyyy | Days dedicated | %Completed | Week of Wednesday: | time axis 2016-04-13 to 2017-06-07
Workplan Draft (Objectives, Significance, Deliverables and Budget) for COBI and Bren | 2016-04-14 | 2016-04-20 | 6 | 100 | bar: 2016-04-13 to 2016-04-20
Summer internship work plan for COBI (April 20th) | 2016-04-17 | 2016-04-22 | 5 | 100 | bar: 2016-04-20
Provide deadlines for deliverables to mark our progress (April 20th) | 2016-04-14 | 2016-04-22 | 8 | 100 | bar: 2016-04-20
List of indicators and a 200 word description of why we chose them | 2016-04-20 | 2016-04-29 | 9 | 50 | bar: 2016-04-20 to 2016-04-27
Finalize selection of external advisors | 2016-04-14 | 2016-05-06 | 22 | 50 | bar: 2016-04-20 to 2016-05-04
Meeting in Mexico City to help COBI consolidate its databases | 2016-05-09 | 2016-05-12 | 3 | 0 |  | 2016-05-11: JC+COBI
Acquire at least a description of COBI’s metadata | 2016-05-12 | 2016-05-15 | 3 | 25 | bar: 2016-05-11
Finalize selection of indicators through expert review | 2016-05-09 | 2016-05-27 | 18 | 0 | bar: 2016-05-11 to 2016-05-25
Design survey for fishers (if needed) or COBI staff (governance) | 2016-05-09 | 2016-05-27 | 18 | 0 | bar: 2016-05-11 to 2016-05-25
Submit draft of Work Plan to Bren School | 2016-04-20 | 2016-05-04 | 14 | 0 | bar: 2016-04-20 to 2016-05-04
Revised Work Plan to faculty advisors, client, and external advisors (May 20th) | 2016-04-20 | 2016-05-20 | 30 | 0 | bar: 2016-05-11 to 2016-05-18
Spring Work Plan Review Meeting with faculty advisors, client, and external advisors | TBD | TBD | #VALUE! | 0 | bar: 2016-06-01
One-page summary of Work Plan Review Meeting (June 10th) | 2016-06-01 | 2016-06-10 | 9 | 0 | bar: 2016-06-01 to 2016-06-08
Final Work Plan to faculty advisors, client and external advisors (June 10th) | 2016-05-25 | 2016-06-10 | 16 | 0 | bar: 2016-05-25 to 2016-06-08
Submit website (June 10th) | 2016-04-20 | 2016-06-10 | 51 | 0 | bar: 2016-04-13 to 2016-06-08
Progress report for COBI | 2016-06-01 | 2016-06-10 | 9 | 0 | bar: 2016-06-01 to 2016-06-08
Self/peer evaluation (June 10th) | 2016-06-10 | 2016-06-10 | 0 | 0 | bar: 2016-06-08
Fill in data gaps by talking with COBI employees, local fishers, and external advisors | 2016-06-13 | 2016-09-07 | 86 | 0 |  | 2016-06-15: JC's Summer Internshhip
Survey fishers (if needed) or COBI staff | 2016-06-13 | 2016-09-07 | 86 | 0 | bar: 2016-06-15 to 2016-09-07
Finalize data acquisition from COBI | 2016-06-13 | 2016-09-07 | 86 | 0 | bar: 2016-06-15 to 2016-09-07
Start working on data | 2016-08-03 | 2016-09-14 | 42 | 0 | bar: 2016-08-03 to 2016-09-14
Regroup and re-evaluate our progress and work plan | 2016-09-19 | 2016-09-23 | 4 | 0 | bar: 2016-09-21
Start outlining data analyses we will perform | 2016-09-19 | 2016-09-23 | 4 | 0 | bar: 2016-09-21
Select cases to be used as examples | 2016-09-19 | 2016-09-23 | 4 | 0 | bar: 2016-09-21
Progress report to COBI | 2016-09-19 | 2016-09-23 | 4 | 0 | bar: 2016-09-21 to 2016-09-28
Visit a fishing community with advisor to help fill-in data gaps/learn more about COBI | TBD | TBD | #VALUE! | 0 |  | 2016-11-02: One of these weeks, TBD
Perform data analysis (i.e. Application of indicators) | 2016-09-21 | 2016-11-18 | 58 | 0 | bar: 2016-09-21 to 2016-11-16
Fall Review Meeting with faculty advisors, client and external advisors (November 18th) | 2016-10-18 | 2016-11-18 | 31 | 0 | bar: 2016-11-16
One-page summary of Fall Review Meeting (November 23rd) | 2016-11-18 | 2016-11-23 | 5 | 0 | bar: 2016-11-16 to 2016-11-23
OUTLINE of final report | 2016-11-18 | 2016-11-23 | 5 | 0 | bar: 2016-11-23
Self/peer evaluation (December 9th) | 2016-12-09 | 2016-12-09 | 0 | 0 | bar: 2016-12-07
Progress report to COBI | 2016-12-05 | 2016-12-09 | 4 | 0 | bar: 2016-12-07
Draft of Final Report to COBI and academic advisor (February 15th) | 2016-11-30 | 2017-02-15 | 77 | 0 | bar: 2016-11-30 to 2017-02-15
Submit our report to experts for review |  |  | 0 | 0
Feedback of Final report | 2017-02-15 | 2017-03-01 | 14 | 0 | bar: 2017-02-15 to 2017-02-22
Prepare for our academic defense | 2017-02-22 | 2017-03-08 | 14 | 0 | bar: 2017-02-22 to 2017-03-08
Final version of Final Report (March 24th) | 2017-03-01 | 2017-03-22 | 21 | 0 | bar: 2017-03-01 to 2017-03-22
Submit Abstract for Final Presentation (March 24th) | 2017-03-01 | 2017-03-22 | 21 | 0 | bar: 2017-03-01 to 2017-03-22
Work on drafting Project Brief | 2017-02-15 | 2017-03-22 | 35 | 0 | bar: 2017-02-15 to 2017-03-22
Work on drafting guidebook | 2017-02-15 | 2017-03-22 | 35 | 0 | bar: 2017-02-15 to 2017-03-22
Progress report to COBI | 2017-02-08 | 2017-02-15 | 7 | 0 | bar: 2017-02-08 to 2017-02-15
Self/Peer evaluation (March 24th) | 2017-03-24 | 2017-03-24 | 0 | 0 | bar: 2017-03-22
Draft of Guidebook to COBI | 2017-01-11 | 2017-04-12 | 91 | 0 | bar: 2017-01-11 to 2017-04-12
Submit Project Brief draft (April 14th) | 2017-04-03 | 2017-04-14 | 11 | 0 | bar: 2017-04-05 to 2017-04-12
Submit Project Poster draft (April 14th) | 2017-04-03 | 2017-04-14 | 11 | 0 | bar: 2017-04-05 to 2017-04-12
Take picture with faculty advisor for Final Presentation (1-2 weeks before April 28th) | 2017-04-03 | 2017-04-14 | 11 | 0 | bar: 2017-04-05 to 2017-04-12
Submit draft of Final Presentation (1-2 weeks before April 28th) | 2017-04-03 | 2017-04-14 | 11 | 0 | bar: 2017-04-05 to 2017-04-12
Submit Final Project Brief and Project Poster (April 24th) | 2017-04-14 | 2017-04-24 | 10 | 0 | bar: 2017-04-19 to 2017-04-26
Final Presentation (April 28th) | 2017-04-14 | 2017-04-24 | 10 | 0 | bar: 2017-04-19 to 2017-04-26
COBI reviews guidebook | 2017-04-14 | 2017-04-24 | 10 | 0 | bar: 2017-04-12 to 2017-04-26
Modify guidebook and translate to spanish | 2017-04-24 | 2017-05-24 | 30 | 0 | bar: 2017-05-03 to 2017-05-24
Progress report to COBI | 2017-04-22 | 2017-04-24 | 2 | 0 | bar: 2017-05-24
Write and submit peer-review paper (Marine Policy?) | 2017-01-04 | 2017-05-24 | 140 | 0 | bar: 2017-01-04 to 2017-05-24
Literature Review | 2016-04-13 | 2017-04-19 | 371 | 5 | bar: 2016-04-13 to 2017-04-12
Note on E23: Caio: I'd say that our work is 50% done now. Basically we have the information, just need to make it look cool.
Note on G23: Caio: I think the website can be a group effort.
Note on W29: Caio: